## Sheet1
Number | Priority | Analysis task | Description | Motivation | Primary source | Notes | Deadline | Status
| H | SDD tail investigation | Zoom in on a few of the long delays that SDD suggested when the actual departure shows there was no delay required | Quick win and Irene is on top of the SDD data now, make sense to clear this one | Compass |  | 2019-04-10 | Done
1 | H | Out of port maintenance (flexible port) | Determine how often a maintenance placard was cancelled, then replaced by another port OR a station break with maintenance was left in the program | Scope discussion around maintenance | Compass | some data cleaning still to do. Notes placards filtered out by looking for keywords. Main ports filtering required. | Mid May | in progress
2 | H | NDS dashboard | Reporting dashboard of NDS usage/performance |  | Compass | Dependency on KPI ticket in Sprint 3.25 | To be discussed with 1A
3 | M/H | Number of commodities in the past | Test the logic proposed for the commodity generation on past instances to determine how many commodities you would end with | Get a feeling for the number of commodities required; Potentially impacts optim method selection | Compass (.aao files?) | Github #5429 | Mid June
4 | M/H | Swap within 45/60 mins from departure | Link to AOG? | Scope discussion around maintenance | Compass | good short intro
5 | M | DC violations not respected | How often did flights take off with a DC violation on them? | Give a first feeling for number of exceptions to constraints / assumption we can make in optim | Compass | Could require using BR module in java - can complicate it. Ref data Json pulled already, should be ok
BACKLOG
| M | Critical links in the past | Expand complexity step-wise. Start by just looking at flights pairs that have never been broken without considering disruption, then adding in disruption complexity etc. | Ability to decrease decision variables in all optim methods | CDW
| M | AOG duration compared to initial guess | At creation of the event, start & end date are filled in. Check how often this gets extended/shortened | Understand complexity/frequency of AOG solutions | Compass
| M | AOG recovery time | Look at changes in time window between AOG start and AOG recovered - assume these changes were required for recovery | Understand complexity/frequency of AOG solutions | Compass
| M | Variable reduction when only looking at feasible combinations | Instead of setting up an n x n matrix of all flight combinations, see how much the size of the problem decreases when you only consider flight pairs without station breaks in them | Ability to decrease decision variables in all optim methods | Compass (.aao files?)
| L | Swap-ability international/domestic | Simple check how often we swap between int/dom | Scope discussion | Compass
| L | Swap-ability mainline/Qlink/Jetstar | Simple check how often we swap between ops centres or even Jetstar | Scope discussion | Compass
| L | SDD bugs? | Identify strange outliers in data and investigate what's going on |  | Compass
drop to lower | M/H | Criticality of maintenance placards | Compass title level and workpackage level | Scope discussion around maintenance | Maintenix | process change may reduce relevanc eof this
drop to lower | L (but high value) | Broken crew connection (mct) | TBD | Give a first feeling for number of exceptions to crew constraints / assumption we can make in optim | TBD - potentially require crewing data from outside Compass | Challenging: first brainstorm about how to tackle & identify data source | Early May | De-prioritised